{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["开发部"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"开发部","index":0,"n_rows":20,"n_cols":13,"rows_kept":20,"cut":false,"hidden":false,"merged":[[2,0,2,4],[2,5,2,8],[2,9,2,12],[3,6,3,8],[5,2,5,5],[6,2,6,5],[7,2,7,5],[8,2,8,5],[9,2,9,5],[10,2,10,5],[11,2,11,5],[12,2,12,5],[13,2,13,5],[14,2,14,5],[15,2,15,5],[16,2,16,5],[17,2,17,5],[18,2,18,5],[19,2,19,5],[3,0,4,0],[5,0,14,0],[15,0,19,0],[3,1,4,1],[3,9,4,9],[3,10,4,10],[3,11,4,11],[3,12,4,12],[0,0,1,12],[3,2,4,5]]}
["拓恒研究院技术中心-开发部-工作周报"]
[]
["部门：      技术部",{"$nulls":4},"姓名：宗金龙",null,null,null,"工作周期：09月14日-09月19日"]
["类别","序号","工作内容",null,null,null,"完成情况（在相应栏打√）",null,null,"工作成果","未完成原因","计划完成时间","需要得到的协助"]
[{"$nulls":6},"已完成","未完成","实施中"]
["本周工作完成情况",1,"优化水务APP项目API接口，提高查询速度和性能",null,null,null,"√",null,null,"已完成"]
[null,2,"搭建水务APP二期迭代项目框架，增加扩展性",null,null,null,"√",null,null,"已完成"]
[null,3,"提前准备水务二期后台项目业务框架的搭建",null,null,null,"√",null,null,"已完成"]
[null,4]
[null,5]
[null,6]
[null,7]
[null,8]
[null,9]
[null,10]
["下周工作计划",1,"南京水务二期APP后期项目规划"]
[null,2]
[null,3]
[null,4]
[null,5]